## Initial Project Plan
Service Tracker Online
Project Plan
Task ID | Task Description | Due | Required Material
0.1 | Project Client Identified | 2019-02-21
Milestone 1
1.1 | Executive Summary | 2019-03-07 | n/a
1.2 | Business Case Summary | 2019-03-07 | n/a
1.3 | Project Plan | 2019-03-07 | n/a
1.4 | Client Contract | 2019-03-07 | n/a
1.5 | Database Diagrams | 2019-03-07 | server use
1.5.1 | Entity Relationship Diagram | 2019-03-07 | server use
1.5.2 | Relation Model | 2019-03-07 | server use
1.6 | Peer Evaluation | 2019-03-07 | n/a
Milestone 2
2.1 | Changes from prior Milestone | 2019-04-11 | n/a
2.2 | Change Memo | 2019-04-11 | n/a
2.2.1 | Written description of changes | 2019-04-11 | n/a
2.2.2 | Updated Project Plan | 2019-04-11 | n/a
2.3 | Preliminary Database | 2019-04-11 | server use
2.3.1 | Table creation scripts | 2019-04-11 | sql
2.3.2 | Screenshot matching ERD | 2019-04-11 | n/a
2.3.3 | Table Population Scripts | 2019-04-11 | sql
2.3.4 | Description of possible queries | 2019-04-11 | n/a
2.3.5 | Description of views | 2019-04-11 | n/a
2.3.6 | Description of users | 2019-04-11 | n/a
2.3.7 | Sketches of front-end | 2019-04-11 | n/a
2.4 | Peer Evaluation | 2019-04-11 | n/a
Milestone 3
3.1 | Changes from prior Milestone | 2019-05-09 | n/a
3.2 | Change Memo | 2019-05-09 | n/a
3.3 | Completed Database | 2019-05-09 | n/a
3.3.1 | SQL for any additional queries | 2019-05-09 | sql
3.3.2 | Description of routines | 2019-05-09 | n/a
3.3.3 | Additional SQL | 2019-05-09 | sql
3.4 | Usable Prototype | 2019-05-09 | angularjs/php
3.4.1 | Home page | 2019-05-09 | php
3.4.2 | Pages that perform queries | 2019-05-09 | php
3.4.3 | Value-added features | 2019-05-09 | n/a
3.5 | Additional prototype sketches | 2019-05-09 | n/a
3.6 | Peer Review | 2019-05-09 | n/a